## Slide 1: Campus Return Plan Bret Watson VP Finance & Administrative Services
May 7, 2020

## Slide 2: Highlights
District Plan
Campus Groups
R & R Council Role

## Slide 3: District Return to Campus Plan
Phased Approach
District Leads - Campuses Coordinate with District
Follow State and County Guidelines

## Slide 4: District Plan cont’d
  Pre-planning Phase – about 30 days to prepare
  Identify Buildings and classrooms opening first
  Specialized Equipment Needed (Protective glass partitions)
  Acquire PPE
      Face masks (FDA Certified/Cal OHSA)
      Gloves
      Hand sanitizer
      Bio Hazzard Containers
      Shipping and Receiving Issues
Phase I - Get Classes/Service Areas Ready
    Clean classes/service areas
    Hand sanitizer for classes/service areas (Gel in and Gel out)
    Protective Panels installed (Dental Hygiene/Assisting)
    Sneeze Guards for front-line employees
    Messaging to prepare for programs/areas returning

## Slide 5: District Plan Cont’d.
Phase II – Bring some instructional programs back to campus (ie - labs) and some support services.
  Manage staffing levels – low at first
  Maintain social distancing
  Have safety protocols/posted messaging
  Cleaning schedule (before and after classes)
Phase III – Bring more instructional programs back (face-to-face) to campus and phase in additional support services.
  Marked spots on the ground for student lines
  Parking
  Buses
  Food Services/KJ’s Coffee?
  Bookstore?
Phase IV – Campus Programs are back and support services and personnel to support students.
  Protocols in place if there are any cases of the coronavirus
    Specialized Contracted Cleaning (all locations that infected person visited)
    Quarantine of exposed faculty, staff, students
    Return Policy in coordination with County

## Slide 6: Campus Plan
List of Buildings, Classrooms, and restrooms to open during the early phases.
Order specialized equipment (sneeze guards, safety shields/partitions)
Order PPE for instructional, service and other personnel areas.
  Gel
  Hand sanitizer
  Gloves
  Wipes/cleaner

## Slide 7: Campus Plan cont’d
Coordinate/Consolidate Groups working on Return Plan
    Instructional Group (Kristy Lisle)
      Labs (Respiratory Therapy, EMT, & Radiology, etc.)
      Athletics (Mike Teijeiro)
    Facilities Group (Bret Watson)
    Student Services

## Slide 8: Revenue & Resource Council Role:
R & R Council Meeting May 8
  Form a Study Group?
  Goals would include:
    Help Develop Campus Plan
    Consolidate groups
    Work with District

## Slide 9
Questions?